## Executive Summary
Retail Expansion — Gap Analysis
Kirana AI -> multi-vertical retail platform ¦ 2026-06-15
Objective | Expand the Kirana AI app + backend from Indian grocery (kirana) to all other retail verticals, EXCEPT medical/pharmacy.
Verticals IN | Apparel / Clothing, Footwear, Electronics / Mobile, Stationery / Books, Hardware / Paint, Cosmetics / Beauty, Toys / Gifts, Home & Kitchenware, General / Variety stores
Vertical OUT | Medical / Pharmacy (drug licence, scheduled drugs, prescriptions, mandatory batch+expiry — high regulatory burden, explicitly excluded)
Headline | The platform is ~80% architecturally generic (auth, orders, customers, procurement, payments, baskets, customer pricing, credit/udhaar) but the product/inventory model, catalog, KPIs, ML, AI prompts, Vision and copy are grocery-coded.
Keystone gap | There is no 'vertical' concept driving behaviour. store_type exists but is dormant. Everything else hangs off building a Vertical Config layer + a product variant/attribute model.
Biggest blockers (P0) | Vertical config; product variant matrix (size x colour); dynamic attributes; make expiry/loose/weight optional; vertical unit registry; tax/GST engine applied at POS; variant-aware POS; backward-compatible migration.
Recommended approach | Config-driven 'vertical packs' (one codebase), NOT per-vertical forks. One vertical dimension drives features, units, attributes, KPIs, ML profile, AI prompts, tax and copy.
Phasing | P0 Foundation (~4-6 wks) -> P1 Apparel pilot (~6-8 wks) -> P2 Electronics (~6-8 wks) -> P3 scale & polish (ongoing).
Counts | 34 gaps logged across 22 themes. See 'Gap Register'. Feature coverage in 'Feature x Vertical Matrix'. Plan in 'Phased Roadmap'. Schema in 'Proposed Data Model'.
Why pharmacy is excluded | Drug licensing, scheduled drugs, prescription workflows and mandatory batch+expiry create a heavy, separate regulatory product — out of scope by design.
Priority legend
P0 = foundational blocker
P1 = needed for first non-grocery verticals
P2 = scale / polish

## Gap Register
ID | Theme | Layer | Current (grocery-specific) state | Gap / impact | Required change | Verticals affected | Priority | Effort | Evidence (file refs)
G-01 | Vertical config | Backend+FE+DB | store.store_type exists (default 'kirana') but branches NO behaviour; app is grocery-first everywhere. | There is no notion of a 'vertical' that drives features, units, KPIs, copy, ML or tax. Every vertical sees grocery UI/logic. | Introduce a Vertical Config layer (per store/vertical): a feature-flag + config object that drives enabled features, unit registry, attribute schema, KPI set, ML profile, tax profile and copy pack. Single keystone that unlocks the rest. | All | P0 | XL | ensure_full_schema.py:59 store_type; no 'WHERE store_type=' branching anywhere
G-02 | Onboarding | Frontend+Backend | Onboarding store-type list is grocery-flavoured: kirana / general / provision / fruits_vegetables / pharmacy / stationery / other. | Missing apparel, footwear, electronics, hardware, cosmetics; choice is cosmetic (stored, never used). No sub-vertical or attribute config captured. | Replace with a real vertical picker that maps to a Vertical Config; capture sub-type + unit/attribute defaults; gate onboarding copy by vertical. | All | P0 | M | onboarding/views/steps/business_step.dart:14-22
G-03 | Vertical config | Frontend | Expiry, loose-weight, perishable and weight-variant UI are always shown. | Non-grocery users see irrelevant fields (expiry pickers, 'sold by weight (e.g. Maida, Pulse)'). | Feature-flag every grocery-only widget; render by vertical (expiry/loose OFF for apparel/electronics/stationery/hardware; optional for cosmetics). | All non-grocery | P0 | M | add_product_sheet.dart perishable/expiry; app_en.arb:919 invLooseItemSub
G-04 | Product data model | DB+Backend+FE | No variant matrix. 'Variants' today are separate product rows differing by weight (1kg vs 500g) each with its own product_id. | Apparel/footwear need ONE product with a grid of size x colour variants; today this is impossible without exploding the catalog and breaking reporting. | Add product_variant table (variant_id, product_id, sku, barcode, attributes, price, mrp, cost, stock); inventory & orders reference variant; FE size x colour grid. | Apparel, Footwear, Cosmetics, Electronics | P0 | XL | pos_product.dart; add_product_sheet.dart _VariantData (weight-based)
G-05 | Product data model | DB+Backend+FE | Product attributes are a fixed grocery set (unit, weight, is_loose, is_perishable, barcode, mrp). | No way to store size, colour, material, RAM/storage, shade, dimensions, model etc. per vertical. | Add a dynamic attribute schema (product_attribute_def per vertical + values on product/variant). Drives add-product form and filters. | All non-grocery | P0 | L | ensure_full_schema.py product table 111-127
G-06 | Product data model | DB+Backend+FE | No serial / IMEI tracking (unit-level identity). | Electronics/mobile must track each unit (serial/IMEI) for sale, warranty and returns. | Add product_serial (serial/imei, status, warranty_until); POS sells a specific serial; receive/return by serial. | Electronics | P1 | L | no serial column in product/inventory
G-07 | Product data model | DB+Backend+FE | No warranty concept. | Electronics, some hardware/appliances sell with warranty (months / tiers / RMA). | Add warranty fields (warranty_months, warranty_until) + optional warranty-tier pricing; surface on bill + returns. | Electronics, Hardware | P1 | M | no warranty fields anywhere
G-08 | Inventory | DB+Backend | Perishable / batch / expiry is first-class (inventory_batch.expiry_date NOT NULL, markdown, waste). | Non-grocery has no expiry; mandatory batch+expiry is wrong for apparel/electronics/stationery/hardware. | Make batch/expiry optional & vertical-gated; per-variant stock; keep for grocery & (optional) cosmetics. | All non-grocery | P0 | M | ensure_full_schema.py inventory_batch 657-671 (expiry_date NOT NULL)
G-09 | Units of measure | Frontend+Backend | Units hardcoded: pcs, kg, g, L, ml, dozen, pack, box, bundle; loose auto-switches to kg. | Apparel needs piece/pair/set; electronics unit/box; hardware m/ft/pack; the grocery list is noise elsewhere. | Vertical-aware unit registry (backend-driven); default per vertical; remove grocery example copy. | All | P0 | M | add_product_sheet.dart:17 _units; app_en.arb:919
G-10 | Pricing & Tax | DB+Backend+FE | GST is parsed from supplier invoices but NEVER applied at pricing/POS; no tax bracket logic; pricing table has no tax column. | Higher-value verticals need compliant tax: apparel 5%/12% by INR1000 threshold, footwear similar, electronics 18%/28%, grocery 0%/5%. | Add tax engine: HSN/category + price-threshold -> GST rate; product.gst_rate/hsn; apply at checkout; show tax breakup on bill & receipt. | All (compliance) | P0 | L | ai/routes.py invoice prompt parses GST; pricing table has no tax (ensure_full_schema.py 150-160)
G-11 | Pricing & Tax | DB+Backend | Cost & price are per product, not per variant; cost lives in product_supplier. | Apparel cost/price varies by size/colour; electronics by model/config. | Move price/mrp/cost to variant level; keep product-level fallback. | Apparel, Footwear, Electronics | P1 | M | pricing table product-level (ensure_full_schema.py 150-160)
G-12 | Pricing & Tax | Backend+FE | Markdown/clearance is expiry-driven (sell before expiry). | Apparel/footwear need season/end-of-line markdown engine (not expiry). | Add season/markdown pricing (planned price drops, clearance flags) decoupled from expiry. | Apparel, Footwear, Cosmetics | P2 | M | near_expiry markdown flow; inventory_batch.markdown_pct
G-13 | KPIs & analytics | Backend | KPI registry is grocery-coded: perishable-waste, dead-stock@21d, category-mix, festive-uplift, daily-velocity assumptions. | These mislead or N/A for other verticals; dead-stock@21d wrongly flags healthy slow-movers (denim, laptops). | Vertical KPI sets selected by Vertical Config; per-vertical thresholds/windows. | All non-grocery | P1 | L | kpis/registry.py; calculator.py calc_perishable_waste / calc_dead_stock
G-14 | KPIs & analytics | Backend | No apparel KPIs. | Apparel needs sell-through %, size-curve / size availability, season & markdown %, GMROI. | Implement apparel KPI pack. | Apparel, Footwear | P1 | M | missing
G-15 | KPIs & analytics | Backend | No electronics KPIs. | Electronics needs attach-rate, warranty-claim %, GMROI, model lifecycle, serial ageing. | Implement electronics KPI pack. | Electronics | P1 | M | missing
G-16 | KPIs & analytics | Frontend+Backend | Dashboard / intelligence copy is grocery-shaped ('critical SKUs', 'reorder today', stockout-risk strip). | Wrong tone/metrics for other verticals. | Vertical-aware dashboard copy & recommendation types. | All non-grocery | P1 | M | app_en.arb dashBriefing*/dashMetric*; recommendation_model.dart
G-17 | ML / forecasting | ML | Demand/stockout/deadstock/velocity models tuned for grocery daily velocity & perishability. | Apparel is seasonal & size-curve driven; electronics slow & high-value; grocery thresholds misfire. | Per-vertical ML profiles (features, windows, thresholds); seasonal models for apparel; cold-start heuristics for new stores. | All non-grocery | P1 | XL | ml_models/models/deadstock_detector.py DEAD_STOCK_DAYS=21; sku_velocity percentiles
G-18 | ML / forecasting | ML+Backend | Models are global, not vertical-scoped. | Cannot load apparel/electronics model variants. | Vertical-scoped model artefacts + config; selection via Vertical Config. | All non-grocery | P1 | M | ml_models config global
G-19 | AI intake (voice/handwrite) | Backend | Voice & handwrite Gemini prompts hardcode grocery dictionaries (rice/dal/atta/oil in TE/HI/...). | No grounding for jeans/saree/shirt/size-32 or mobile/laptop/warranty. | Vertical-aware prompts + ground against the store's own catalog/variants instead of a fixed grocery glossary. | All non-grocery | P1 | M | ai/routes.py:299-372 _VOICE_PROMPT/_HANDWRITE_PROMPT
G-20 | AI intake (invoice) | Backend | Invoice OCR prompt is grocery-flavoured (MRP-on-packet, snack examples). | Apparel/electronics invoices carry size/colour/serial/warranty per line. | Vertical invoice prompt variants; map to variants/serials. | Apparel, Electronics | P1 | M | ai/routes.py:374-441 _INVOICE_PROMPT
G-21 | Vision | Backend+FE | Vision shelf-scan + Gemini prompt are grocery-specific ('kirana shelf', readable package text, morning/evening cadence). | Apparel is folded/hung with no readable text; electronics are boxed/barcoded; shelf-scan won't recognise them. | Gate Vision by vertical (off where unsupported); medium-term redesign capture per vertical (rack/box/barcode); retrain per vertical. | Apparel, Electronics, others | P1 | L | vision/analyzer.py SHELF_PROMPT 'kirana store shelf'; vision_provider.dart shelf/analyze
G-22 | POS & billing | Frontend | POS add-to-cart assumes loose weight dialog (decimal kg) or single discrete unit. | Non-grocery needs variant selection (size/colour, model, serial) before add; no weighing. | Variant-aware add-to-cart (pick size/colour/serial); hide weight dialog where not loose. | Apparel, Footwear, Electronics | P0 | M | pos_tab.dart:66-130 _showWeightDialog
G-23 | POS & billing | Frontend+Backend | Bill / thermal receipt has no tax breakup. | Higher-value verticals & GST compliance need tax on the invoice/receipt. | Add tax lines to bill + printer template (ties to G-10). | All | P1 | M | printer receipt template; pos order
G-24 | Copy & branding | Frontend (l10n) | 'Kirana AI' brand + grocery examples (Maida/Pulse), 'mykiranastore' hints, grocery welcome/consent copy across 7 ARBs. | Apparel/electronics users see grocery branding & nonsensical examples. | Neutral / white-label or vertical-aware copy pack; parameterise brand & examples; re-translate the delta across 7 languages. | All non-grocery | P1 | L | app_en.arb:22,49,132,178,919,157
G-25 | WhatsApp | Backend | WhatsApp menu buttons/templates hardcode grocery KPIs (Stockout, Fast-Moving SKUs) per language. | Apparel/electronics owners want different metrics & flows. | Vertical-aware WhatsApp menus/templates selected by Vertical Config. | All non-grocery | P2 | M | whatsapp/templates.py:48-66 ANALYTICS_BUTTONS
G-26 | Catalog | Backend+Data | Catalog = ~11k grocery blinkit SKUs (KAI-{blinkitId}); add-product leans on it. | Other verticals have no seed catalog; manual add is slow without barcode/catalog support. | Barcode lookup (global) + per-vertical catalog ingestion + fast manual add with attribute templates. | All non-grocery | P1 | L | db_generation/seed_blinkit_catalog.py; vision/matcher.py loads all product
G-27 | Catalog | Backend | Catalog matcher loads ALL products in-memory; no vertical partition. | Apparel/electronics with variants reach 50k+ rows; in-memory match doesn't scale & mixes verticals. | Partition catalog by vertical; move to indexed / vector search for large catalogs. | Apparel, Electronics | P2 | L | vision/matcher.py:21-93 SELECT all product
G-28 | Procurement | Backend+FE | Supplier/PO model is generic but date-based; no MOQ, lead time, seasonal/size-pack buying. | Apparel buys by season/size-pack; electronics receive by serial; reorder logic differs. | Extend procurement with MOQ, lead time, season; serial receipt for electronics. | Apparel, Electronics, Hardware | P2 | M | procurement_models.dart; purchases table
G-29 | Customer | DB+Backend | customer.household_size (default 4) and grocery referral assumptions. | Irrelevant for apparel/electronics; harmless but noisy. | Make demographic fields optional / vertical-aware; keep generic segments. | All non-grocery | P2 | S | ensure_full_schema.py customer.household_size
G-30 | Credit (udhaar) | Backend+FE | Udhaar/khata credit ledger (KEEP — broadly used across Indian small retail). | NOT a blocker: apparel, hardware, general stores also extend credit. Electronics lean to EMI. | Keep udhaar as a cross-vertical strength; add optional EMI/instalment stub for electronics later. | Electronics (EMI optional) | P2 | S | finance/khata — cross-vertical strength, not a gap
G-31 | Notifications / widget | Frontend | Home widget + push taxonomy surface grocery KPIs (stockout, reorder, fast-moving). | Wrong metrics for other verticals. | Vertical-aware widget stats & notification copy. | All non-grocery | P2 | S | home widget snapshot keys; notification taxonomy
G-32 | Baskets / bundles | Backend+FE | Bundles/baskets are generic but use cases & copy are grocery (food combos). | Minor: works for apparel ('outfit bundles'), needs copy. | Vertical copy for bundles; otherwise reuse as-is (strength). | All | P2 | S | features/baskets — generic engine
G-33 | Reporting / export | Backend+FE | Reports/exports assume grocery categories & units. | Need variant- and tax-aware reporting (size-curve, sell-through, tax summaries). | Variant/tax-aware reports & exports per vertical. | All non-grocery | P2 | M | transaction history; KPI exports
G-34 | Data migration / rollout | Backend+DB | Existing grocery stores run on the current single-product model. | Introducing variants/attributes/tax must not break live grocery stores or order history. | Backward-compatible migration: variant is optional (grocery = single implicit variant); phase behind Vertical Config; verify on staging before deploy. | All | P0 | M | single unified DB kirana_oltp; live grocery stores

## Feature x Vertical Matrix
Feature / capability | Grocery (Kirana) | Apparel | Footwear | Electronics | Stationery | Hardware | Cosmetics | General
Orders & checkout core | Works | Works | Works | Works | Works | Works | Works | Works
Product variants (size x colour) | N/A | Build | Build | Adapt | Optional | Optional | Adapt | Optional
Serial / IMEI tracking | N/A | N/A | N/A | Build | N/A | Optional | N/A | N/A
Expiry / batch tracking | Works | N/A | N/A | N/A | N/A | N/A | Optional | Optional
Loose / weight POS | Works | N/A | N/A | N/A | N/A | Optional | N/A | Optional
Units of measure | Works | Adapt | Adapt | Adapt | Adapt | Adapt | Adapt | Adapt
Tax / GST engine | Build | Build | Build | Build | Build | Build | Build | Build
KPIs / analytics | Works | Build | Build | Build | Adapt | Adapt | Adapt | Adapt
Demand / ML forecast | Works | Build | Build | Adapt | Adapt | Adapt | Adapt | Adapt
Voice / handwrite intake | Works | Adapt | Adapt | Adapt | Adapt | Adapt | Adapt | Adapt
Vision shelf-scan | Works | Build | Adapt | N/A | Adapt | N/A | Adapt | Adapt
WhatsApp assistant | Works | Adapt | Adapt | Adapt | Adapt | Adapt | Adapt | Adapt
Udhaar / credit ledger | Works | Works | Works | Optional | Works | Works | Works | Works
Baskets / bundles | Works | Adapt | Adapt | Adapt | Works | Works | Adapt | Works
Catalog seed | Works | Build | Build | Build | Build | Build | Build | Adapt
Customer mgmt / segments | Works | Works | Works | Works | Works | Works | Works | Works
Procurement / suppliers | Works | Adapt | Adapt | Adapt | Works | Adapt | Works | Works
Customer-specific pricing | Works | Works | Works | Works | Works | Works | Works | Works
Legend: | Works | Adapt | Build | Optional | N/A

## Phased Roadmap
Phase | Timeline | Scope / workstreams | Outcome | Gap IDs
Phase 0 — Foundation (vertical-enable the platform) | ~4-6 weeks | Vertical Config layer + feature flags; dynamic attribute schema + product_variant table (DB+API+core add-product UI); vertical unit registry; tax engine (HSN/threshold -> GST, applied at POS + receipt); neutralise branding/copy scaffolding; backward-compatible migration (grocery = single implicit variant). | Unlocks General/Variety, Stationery, Hardware, Cosmetics with light extra work. | G-01, G-02, G-03, G-04, G-05, G-08, G-09, G-10, G-22, G-24, G-34
Phase 1 — Apparel pilot | ~6-8 weeks | Size x colour variant grid UI; apparel KPI pack (sell-through, size-curve, GMROI, season/markdown); apparel ML profile (seasonal) + cold-start heuristics; vertical copy pack; vision gated off; pilot with a few stores. | First true non-grocery vertical live; validates the model. | G-04, G-11, G-13, G-14, G-16, G-17, G-19, G-21, G-24
Phase 2 — Electronics / Mobile | ~6-8 weeks | Serial/IMEI + warranty; GST 18/28; electronics KPI pack (attach-rate, GMROI, warranty-claim); EMI/instalment stub; invoice prompt v2 (serial/warranty). | High-value vertical with unit-level identity. | G-06, G-07, G-10, G-15, G-20, G-30
Phase 3 — Scale & polish | Ongoing | Per-vertical catalogs + ingestion; catalog partition / vector search; vertical AI prompts & WhatsApp menus; vision redesign per vertical; ML retraining; vertical-aware widget/notifications; reporting/exports. | Breadth across the remaining verticals + quality. | G-12, G-18, G-21, G-25, G-26, G-27, G-28, G-29, G-31, G-32, G-33

## Proposed Data Model
Table | Change | Purpose | Key columns
vertical_config | New | Per vertical (and/or per store): feature flags + config that drive the whole app. | vertical_code, features(jsonb: expiry,loose,variants,serial,warranty...), unit_set, attribute_set, kpi_set, ml_profile, tax_profile, copy_pack
product_attribute_def | New | Dynamic attribute definitions per vertical (drives add-product form + filters). | vertical_code, attr_code, label, type(text¦enum¦number), options, is_variant_axis, sort
product_variant | New (keystone) | One product -> many sellable variants (size x colour, model/config, shade). Grocery = single implicit variant. | variant_id PK, product_id FK, sku, barcode, attributes(jsonb), price, mrp, cost, is_active
product_serial | New | Unit-level identity for electronics (and serialised hardware). | serial_id PK, variant_id FK, serial_no/imei UNIQUE, status(in_stock¦sold¦returned), warranty_until, sold_order_id
tax_rule | New | Category/HSN + price-threshold -> GST rate; applied at checkout. | hsn/category, min_price, max_price, gst_rate; (product gains hsn_code, gst_rate override)
inventory (modify) | Modify | Stock at VARIANT level; batch/expiry optional & vertical-gated. | add variant_id; make batch/expiry nullable; keep product-level for grocery
pricing (modify) | Modify | Price/mrp/cost can live at variant level; add tax columns. | variant_id (nullable), gst_rate/hsn
product (modify) | Modify | Grocery-only columns become optional & vertical-gated. | is_perishable/is_loose/weight nullable; add hsn_code, gst_rate, brand/season as needed
store (modify) | Modify | Activate the dormant store_type into a real vertical_code linked to vertical_config. | vertical_code FK -> vertical_config