## Read me first
How to use this backlog
1. ~80% of rows 'ride a foundation' (F1-F4). Build the 5 F- rows FIRST; then C-/V-/T-/K-/A- rows become config + a form + a query, not new systems.
2. N- rows are genuinely NEW modules Guru surfaced (loyalty, services/appointments, staff ops, multi-store). These do NOT shortcut - schedule after the foundation.
3. Source = who found it: Mine = Retail_Expansion sheet, Guru = his Feature Gap sheet, Both = overlap (assign ONCE).
4. Suggested order: F-01 -> F-02 -> F-05 (migration) -> F-04 -> KPI/ML/AI packs -> remaining C/V/T rows -> N modules.
5. Priority: P0 blocker, P1 first non-grocery verticals, P2 scale/polish. Effort: S/M/L/XL.
See Gap_Fill_Playbook.md for the step-by-step build of each foundation (tables, endpoints, files).

## Combined Gap Backlog
ID | Area | Gap / capability | Source | What to build (developer view) | Layer | Rides foundation | Priority | Effort | Depends on
F-01 | Foundation | Vertical Config layer | Mine | vertical_config table + store.vertical_code + GET /vertical-config + FE provider + feature-flag helper | DB+BE+FE | F1 Vertical Config | P0 | XL | -
F-02 | Foundation | Product variant matrix | Both | product_variant + product_attribute_def; inventory/orders ref variant; grocery=implicit variant | DB+BE+FE | F2 Variants/Attrs | P0 | XL | F-01
F-03 | Foundation | Dynamic attribute schema | Mine | product_attribute_def per vertical drives add-product form + filters | DB+BE+FE | F2 Variants/Attrs | P0 | L | F-01
F-04 | Foundation | Tax / GST engine at POS | Both | tax_rule (hsn/category+threshold to rate); product hsn/gst_rate; apply at checkout; tax lines | DB+BE+FE | F3 Tax engine | P0 | L | F-02
F-05 | Foundation | Backward-compatible migration | Mine | grocery=single implicit variant; phase behind config; verify on staging | DB+BE | - | P0 | M | F-02
C-01 | Inventory | Hide grocery-only UI (expiry/loose/weight) | Mine | feature-flag widgets by vf.has(...) | FE | F1 Vertical Config | P0 | M | F-01
C-02 | Onboarding | Real vertical picker | Mine | picker maps to vertical_code + defaults | FE+BE | F1 Vertical Config | P0 | M | F-01
C-03 | Units | Vertical unit registry | Mine | read vf.unit_set; drop hardcoded grocery units | FE+BE | F1 Vertical Config | P0 | M | F-01
C-04 | Copy | Neutral/vertical copy + brand | Mine | copy_pack drives brand, examples, welcome/consent across 7 langs | FE | F1 Vertical Config | P1 | L | F-01
C-05 | Customer | Vertical-aware demographic fields | Mine | household_size etc optional by config | DB+BE | F1 Vertical Config | P2 | S | F-01
C-06 | Widget/Notif | Vertical widget stats & copy | Mine | config-driven snapshot keys + notif copy | FE | F1 Vertical Config | P2 | S | F-01
C-07 | Baskets | Vertical bundle copy | Mine | reuse engine; copy per vertical (outfit bundles) | FE | F1 Vertical Config | P2 | S | F-01
V-01 | Inventory | Variant mgmt (size/colour/style) | Both | size x colour grid in add-product | FE | F2 Variants/Attrs | P0 | L | F-02
V-02 | POS | Variant-aware add-to-cart | Both | pick size/colour/serial before add; hide weight dialog | FE | F2 Variants/Attrs | P0 | M | F-02
V-03 | Pricing | Per-variant price/mrp/cost | Mine | move price to variant; product fallback | DB+BE | F2 Variants/Attrs | P1 | M | F-02
V-04 | Inventory | Serial / IMEI tracking | Both | product_serial child table; sell/return by serial | DB+BE+FE | F2 Variants/Attrs | P1 | L | F-02
V-05 | Inventory | Warranty | Mine | warranty_months/until; show on bill + returns | DB+BE+FE | F2 Variants/Attrs | P1 | M | F-02
V-06 | Inventory | Make expiry/batch optional | Mine | nullable + vertical-gated; per-variant stock | DB+BE | F2 Variants/Attrs | P0 | M | F-02
V-07 | Catalog | Per-vertical catalog + barcode lookup | Both | barcode lookup + ingestion + fast manual add | BE+Data | F2 Variants/Attrs | P1 | L | F-02
V-08 | Catalog | Partition catalog / vector search | Mine | stop loading all products in-memory; index by vertical | BE | F2 Variants/Attrs | P2 | L | F-02
T-01 | Billing | Tax lines on bill + thermal receipt | Both | add tax breakup to receipt template | FE+BE | F3 Tax engine | P1 | M | F-04
K-01 | Analytics | Per-vertical KPI sets | Mine | tag KPIs by vertical; dashboard reads vf.kpi_set | BE | F4 KPI/ML/AI packs | P1 | L | F-01
K-02 | Analytics | Apparel KPI pack | Mine | sell-through, size-curve, GMROI, markdown% | BE | F4 KPI/ML/AI packs | P1 | M | K-01
K-03 | Analytics | Electronics KPI pack | Mine | attach-rate, warranty-claim, GMROI, serial ageing | BE | F4 KPI/ML/AI packs | P1 | M | K-01
K-04 | Analytics | Category / brand analytics | Guru | brand-wise performance reports | BE+FE | F4 KPI/ML/AI packs | P1 | M | K-01
K-05 | Analytics | P&L with COGS detail | Guru | margin-accurate P&L (needs tax+cost) | BE | F4 KPI/ML/AI packs | P1 | M | F-04
K-06 | ML | Per-vertical ML profiles | Mine | features/windows/thresholds per vertical; seasonal apparel; cold-start | ML | F4 KPI/ML/AI packs | P1 | XL | F-01
K-07 | ML | Vertical-scoped model artefacts | Mine | load model by vertical via config | ML+BE | F4 KPI/ML/AI packs | P1 | M | K-06
K-08 | ML | Demand forecasting (seasonal) | Both | festival/wedding peaks | ML | F4 KPI/ML/AI packs | P1 | M | K-06
K-09 | ML | Price optimisation | Both | competitor-aware dynamic pricing | ML+BE | F4 KPI/ML/AI packs | P2 | L | K-06
K-10 | ML | Anomaly / shrinkage (more segments) | Both | extend detection beyond grocery | ML+BE | F4 KPI/ML/AI packs | P2 | M | K-06
K-11 | ML | Personalised suggestion | Both | recommender from past purchases | ML+BE | F4 KPI/ML/AI packs | P1 | M | K-06
A-01 | AI intake | Vertical voice/handwrite prompts | Mine | ground against store catalog not grocery glossary | BE | F4 KPI/ML/AI packs | P1 | M | F-01
A-02 | AI intake | Vertical invoice prompt | Mine | map size/colour/serial/warranty lines | BE | F4 KPI/ML/AI packs | P1 | M | F-01
A-03 | Vision | Gate vision by vertical | Mine | off where unsupported; redesign capture later | BE+FE | F4 KPI/ML/AI packs | P1 | L | F-01
N-01 | Billing/CRM | Loyalty / points programme | Guru | points, tiers, redemption engine | DB+BE+FE | (new module) | P0 | L | -
N-02 | CRM | Birthday / anniversary offers | Guru | automated trigger campaigns | BE+FE | (new module) | P0 | M | N-01
N-03 | Services | Appointments + calendar | Guru | booking/calendar for saloon/optical/fitness | DB+BE+FE | (new module) | P0 | XL | -
N-04 | Services | Membership / package billing | Guru | prepaid packages, sessions | DB+BE+FE | (new module) | P0 | L | N-03
N-05 | Staff | Commission / incentive tracking | Guru | per-staff commission rules | DB+BE+FE | (new module) | P0 | L | -
N-06 | Staff | Attendance & payroll | Guru | multi-staff attendance/payroll | DB+BE+FE | (new module) | P1 | L | -
N-07 | Staff | Shift / schedule + task checklist | Guru | roster planner + opening/closing checklist | BE+FE | (new module) | P1 | M | -
N-08 | Staff | Staff performance report | Guru | per-staff revenue/conversion/commission | BE+FE | (new module) | P1 | M | N-05
N-09 | Multi-store | Zone / city comparison | Guru | multi-store/city dashboard | BE+FE | (new module) | P0 | L | -
N-10 | Multi-store | Footfall / conversion analytics | Guru | footfall counter integration | BE+FE+HW | (new module) | P1 | L | -
N-11 | Inventory | Multi-location / multi-rack stock | Guru | rack/aisle mapping; stock per location | DB+BE | (new module) | P0 | L | -
N-12 | Inventory | Supplier catalogue & price linking | Both | supplier portal + brand catalogue API | BE+FE | (new module) | P1 | L | V-07
N-13 | Orders | PO auto-fill + MOQ/lead time | Both | supplier-linked PO; season/size-pack buying | BE+FE | (new module) | P1 | M | N-12
N-14 | Orders | Online catalogue / WhatsApp ordering | Guru | shareable digital product links | BE+FE | (new module) | P1 | L | V-07
N-15 | Orders | Returns & exchange + reason codes | Both | extend returns flow; variant/tax aware | BE+FE | (new module) | P1 | M | F-02
N-16 | Billing | Discount / coupon management | Guru | category/brand discount rules | BE+FE | (new module) | P1 | M | -
N-17 | Billing | Estimate / proforma invoice | Guru | quotation flow | BE+FE | (new module) | P1 | M | -
N-18 | Billing | Split / partial payment | Both | service+product, frame+lens split | BE+FE | (new module) | P1 | M | -
N-19 | CRM | Customer referral tracking | Both | extend existing referral with codes | BE+FE | (new module) | P2 | S | -
N-20 | Credit | EMI / instalment stub (electronics) | Mine | optional instalment on top of udhaar | BE+FE | (new module) | P2 | S | -